## Sheet1
Requirements |  | Met | Notes
Functionality should reflect the below user stories.
Data is stored in a database. |  | y
Data Access is performed through the use of JDBC in a data layer consisting of Data Access Objects. |  | y
All input is received using the java.util.Scanner class. |  | y
Log4j is implemented to log events to a file. |  | ~ | Currently debugs everything; will want to turn some of this off later
A minimum of 10 JUnit test is written to test some functionality.
User Stories | Points | Met | Notes
As a user, I can register for a customer account (checking or savings or both!). | 3 | ~ | Can register both when signing up; not registering in database when you try to add an account as an existing member
(Stretch goal) As a user, I can apply for a joint account | 3
As a user, I can login. | 2 | y
As a customer, I can apply for a new bank account with a starting balance. | 3 | ~ | Need to validate starting balance
As a customer, I can view the balance of a specific account (that belongs to me). | 1 | y | View balance of all accounts at once on Customer DB
As a customer, I can make a withdrawal or deposit to a specific account (that belongs to me). | 2 | y
As the system, I reject invalid transactions. Ex: A withdrawal that would result in a negative balance. A deposit or withdrawal of negative money. | 2 | ~ | Works for initial setup; working for withdrawal/deposit tbd
As an employee, I can approve or reject an account registration by a user. | 2 | ~ | Works, but can't print username for some reason???
As an employee, I can view a customer's bank accounts. | 1
As a customer, I can post a money transfer to another account. | 3
As a customer, I can accept a money transfer from another account. | 2
An employee, I can view a log of all transactions. | 2
Other |  | Met | Notes
Provide username & password at login |  | y
Be able to log in and out |  | y